## Sheet1
Q1 | Is the project over-budget?If yes, by how many hours? | time(mo) | PV | EV | AC
A1 | Yes, by 1500 hours | 0 | 0 | 0 | 0
Q2 | Is the project delayed? If yes,by how many days? | 3 | 2500 | 1000 | 3000
A2 | 1500 hours/5 Developers=300 hours/developver Assume the developer worrk 10 hours a day Then the poject is delayed by 30 Working Days | 6 | 5000 | 3000 | 6000
|  | 9 | 7500 | 6000 | 8000
|  | 12 | 10000 | 7500