## Sheet1
# | Risk | Probability | Impact | Planning strategy | Action
1 | Software Bugs | H | M | Mitigate | Test the SW continusly
2 | Traning taking much time | M | H | Transfer | Transfer to the client
3 | Hardware delay due to customs | M | M | Avoid | Buy Hardware from local supplier
4 | Delay due to covid 19 lockdown | H | M | Accept | Work remotly